## Sayfa1
Start Date: 29/09/2019 | Assignment |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16
Work Plan
Sprint 1 |  | Week (1-4) | bar: WEEK 1 to WEEK 4
Project Proposal Preliminary Study | Elif Solmaz / Büşra Karausta | bar: WEEK 1 to WEEK 2
Project Proposal Summary | Kenan Özütemiz / Elif Solmaz | bar: WEEK 2 to WEEK 3
Company Meeting (Project Plan) | Team | bar: WEEK 2 to WEEK 4
Project Management System (Trello) | Büşra Karausta | bar: WEEK 3 to WEEK 4
Student-Project Relationship Table | Team | bar: WEEK 4
Sprint 2 |  | Week (5-8) | bar: WEEK 5 to WEEK 8
Literature Search / Field Research | Team | bar: WEEK 5 to WEEK 8
SRS Document | Team | bar: WEEK 6 to WEEK 9
Classification (Level Design) | Büşra Karausta / Kenan Özütemiz | bar: WEEK 7 to WEEK 8
Company Meeting | Team | bar: WEEK 5; WEEK 7 to WEEK 8
Modularity and Chapters | Elif Solmaz / Büşra Karausta | bar: WEEK 6 to WEEK 8
Sprint 3 |  | Week (9-12) | bar: WEEK 9 to WEEK 12
Project Website Design | Büşra Karausta / Elif Solmaz | bar: WEEK 9 to WEEK 10
SDD Document | Elif Solmaz / Kenan Özütemiz | bar: WEEK 10 to WEEK 11
SRS Document Revision | Elif Solmaz | bar: WEEK 10 to WEEK 12
Company Meeting | Tolga Özalp, Utku Özcan | bar: WEEK 11 to WEEK 12
Final |  | Week (12-16) | bar: WEEK 12 to WEEK 16
Company Meeting | Team | bar: WEEK 14 to WEEK 16
SDD Document Revision | Team | bar: WEEK 12 to WEEK 14
Completion of the Project Report | Team | bar: WEEK 13 to WEEK 14
Project Presentation | Team | bar: WEEK 15 to WEEK 16